## Dashboard
PROJECT TRACKER DASHBOARD
Real-Time Project Status Overview
Total Projects |  |  | In Progress |  |  | On Track | At Risk
25 |  |  | 19 |  |  | 19 | 3
Active portfolio |  |  | Currently active |  |  | Green status | Needs attention
Delayed |  |  | Completed |  |  | Avg Progress | Overdue Tasks
3 |  |  | 3 |  |  | 53.84 | 0
Behind schedule |  |  | Finished |  |  | Overall progress | Requires action
PROJECT STATUS SUMMARY
Project Name | Manager | Status | Progress | Start Date | End Date | Days Left
Website Redesign | Sarah Chen | In Progress | On Track | 2024-01-15 | 2024-04-30 | 0
Mobile App v2.0 | Mike Johnson | In Progress | At Risk | 2024-02-01 | 2024-06-15 | 0
CRM Integration | Lisa Wang | In Progress | On Track | 2024-03-01 | 2024-05-31 | 0
Marketing Campaign | Tom Davis | Completed | On Track | 2024-01-01 | 2024-03-15 | 0
Data Migration | Emma Wilson | In Progress | Delayed | 2024-02-15 | 2024-04-15 | 0
Formulas:
On Track = MAX(0,[End Date]-TODAY())

## Project List
PROJECT PORTFOLIO
Project ID | Project Name | Client | Manager | Status | Health | Progress % | Start Date | End Date | Budget ($)
PRJ-001 | Website Redesign | Acme Corp | Sarah Chen | In Progress | On Track | 65 | 2024-01-15 | 2024-04-30 | 45000
PRJ-002 | Mobile App v2.0 | TechStart | Mike Johnson | In Progress | At Risk | 45 | 2024-02-01 | 2024-06-15 | 85000
PRJ-003 | CRM Integration | Global Inc | Lisa Wang | In Progress | On Track | 78 | 2024-03-01 | 2024-05-31 | 62000
PRJ-004 | Marketing Campaign | Retail Co | Tom Davis | Completed | On Track | 100 | 2024-01-01 | 2024-03-15 | 28000
PRJ-005 | Data Migration | Finance Ltd | Emma Wilson | In Progress | Delayed | 35 | 2024-02-15 | 2024-04-15 | 55000
PRJ-006 | E-commerce Platform | ShopNow | Sarah Chen | In Progress | On Track | 52 | 2024-02-20 | 2024-07-30 | 120000
PRJ-007 | HR System Upgrade | MegaCorp | Mike Johnson | Planning | On Track | 15 | 2024-04-01 | 2024-08-31 | 95000
PRJ-008 | Analytics Dashboard | DataViz | Lisa Wang | In Progress | On Track | 88 | 2024-01-10 | 2024-03-31 | 38000
PRJ-009 | Cloud Migration | CloudFirst | Tom Davis | In Progress | At Risk | 40 | 2024-03-15 | 2024-09-30 | 150000
PRJ-010 | Security Audit | SecureNet | Emma Wilson | Completed | On Track | 100 | 2024-01-05 | 2024-02-28 | 32000
PRJ-011 | API Development | APIHub | Sarah Chen | In Progress | On Track | 60 | 2024-02-10 | 2024-05-15 | 48000
PRJ-012 | UX Research | DesignCo | Mike Johnson | In Progress | On Track | 72 | 2024-01-20 | 2024-04-10 | 25000
PRJ-013 | Database Optimization | DBPro | Lisa Wang | In Progress | On Track | 55 | 2024-03-01 | 2024-05-31 | 42000
PRJ-014 | Training Platform | EduTech | Tom Davis | Planning | On Track | 5 | 2024-05-01 | 2024-10-31 | 75000
PRJ-015 | Inventory System | LogiCorp | Emma Wilson | In Progress | Delayed | 30 | 2024-02-01 | 2024-04-30 | 58000
PRJ-016 | Payment Gateway | PayFast | Sarah Chen | In Progress | On Track | 68 | 2024-01-25 | 2024-04-25 | 52000
PRJ-017 | Chatbot Development | AI Solutions | Mike Johnson | In Progress | On Track | 48 | 2024-03-10 | 2024-06-30 | 65000
PRJ-018 | Email Marketing Tool | MailPro | Lisa Wang | Completed | On Track | 100 | 2024-01-15 | 2024-03-20 | 35000
PRJ-019 | Video Platform | StreamCo | Tom Davis | In Progress | At Risk | 25 | 2024-03-01 | 2024-08-15 | 110000
PRJ-020 | Blockchain Integration | CryptoFin | Emma Wilson | Planning | On Track | 8 | 2024-05-15 | 2024-11-30 | 180000
PRJ-021 | Social Media App | SocialHub | Sarah Chen | In Progress | On Track | 58 | 2024-02-15 | 2024-06-30 | 92000
PRJ-022 | Supply Chain Tool | SupplyCo | Mike Johnson | In Progress | On Track | 42 | 2024-03-05 | 2024-07-15 | 78000
PRJ-023 | Booking System | TravelPro | Lisa Wang | In Progress | On Track | 75 | 2024-01-30 | 2024-04-30 | 45000
PRJ-024 | IoT Dashboard | IoT Solutions | Tom Davis | In Progress | Delayed | 20 | 2024-03-20 | 2024-09-20 | 135000
PRJ-025 | Compliance System | LegalTech | Emma Wilson | In Progress | On Track | 62 | 2024-02-05 | 2024-05-20 | 68000

## Task Tracker
TASK TRACKER & GANTT DATA
Task ID | Task Name | Project | Assignee | Priority | Status | Start Date | Due Date | Duration (Days) | Progress % | Due Status | Notes
TSK-001 | Homepage Design | Website Redesign | Alice | High | Completed | 2024-01-15 | 2024-01-25 | 10 | 100 | Completed | Approved by client
TSK-002 | Product Pages | Website Redesign | Bob | High | In Progress | 2024-01-26 | 2024-02-10 | 15 | 80 | Due Soon | Need product photos
TSK-003 | Checkout Flow | Website Redesign | Alice | Critical | In Progress | 2024-02-05 | 2024-02-25 | 20 | 60 | Due Soon | Payment integration pending
TSK-004 | User Authentication | Mobile App v2.0 | Charlie | Critical | In Progress | 2024-02-01 | 2024-02-20 | 19 | 70 | Due Soon | OAuth implementation
TSK-005 | Push Notifications | Mobile App v2.0 | Diana | Medium | Not Started | 2024-03-01 | 2024-03-15 | 14 | 0 | Due Soon
TSK-006 | Data Sync Module | CRM Integration | Eve | High | In Progress | 2024-03-01 | 2024-03-20 | 19 | 85 | Due Soon | API endpoints ready
TSK-007 | Contact Management | CRM Integration | Frank | High | In Progress | 2024-03-10 | 2024-04-05 | 26 | 50 | Due Soon
TSK-008 | Email Templates | Marketing Campaign | Grace | Medium | Completed | 2024-01-05 | 2024-01-20 | 15 | 100 | Completed | 12 templates created
TSK-009 | Social Media Plan | Marketing Campaign | Henry | Medium | Completed | 2024-01-10 | 2024-02-01 | 22 | 100 | Completed | Q1 plan approved
TSK-010 | Data Backup | Data Migration | Ivan | Critical | In Progress | 2024-02-15 | 2024-03-01 | 15 | 40 | Due Soon | Backup issues detected
TSK-011 | Schema Migration | Data Migration | Julia | Critical | In Progress | 2024-03-01 | 2024-03-25 | 24 | 30 | Due Soon | Complex dependencies
TSK-012 | Shopping Cart | E-commerce Platform | Kevin | High | In Progress | 2024-02-20 | 2024-03-15 | 24 | 65 | Due Soon | Cart logic complete
TSK-013 | Payment Integration | E-commerce Platform | Alice | Critical | Not Started | 2024-03-20 | 2024-04-15 | 26 | 0 | Due Soon | Stripe API setup
TSK-014 | User Dashboard | HR System | Bob | Medium | Not Started | 2024-04-01 | 2024-04-20 | 19 | 0 | Due Soon
TSK-015 | Report Generation | Analytics Dashboard | Charlie | High | In Progress | 2024-01-15 | 2024-02-15 | 31 | 90 | Due Soon | Charts implemented
TSK-016 | Data Export | Analytics Dashboard | Diana | Medium | In Progress | 2024-02-20 | 2024-03-10 | 19 | 75 | Due Soon | CSV/PDF export
TSK-017 | Server Setup | Cloud Migration | Eve | Critical | In Progress | 2024-03-15 | 2024-04-10 | 26 | 35 | Due Soon | AWS configuration
TSK-018 | Security Review | Security Audit | Frank | Critical | Completed | 2024-01-05 | 2024-01-25 | 20 | 100 | Completed | All issues resolved
TSK-019 | API Documentation | API Development | Grace | High | In Progress | 2024-02-10 | 2024-03-01 | 20 | 55 | Due Soon | Swagger setup
TSK-020 | User Interviews | UX Research | Henry | Medium | In Progress | 2024-01-20 | 2024-02-15 | 26 | 80 | Due Soon | 15 interviews done
TSK-021 | Query Optimization | Database Optimization | Ivan | High | In Progress | 2024-03-01 | 2024-03-20 | 19 | 60 | Due Soon | Index analysis
TSK-022 | Course Creation | Training Platform | Julia | Medium | Not Started | 2024-05-01 | 2024-06-15 | 45 | 0 | Due Soon
TSK-023 | Barcode Scanner | Inventory System | Kevin | High | In Progress | 2024-02-01 | 2024-02-28 | 27 | 25 | Due Soon | Hardware compatibility
TSK-024 | Transaction Logging | Payment Gateway | Alice | Critical | In Progress | 2024-01-25 | 2024-02-20 | 26 | 70 | Due Soon | Audit trail complete
TSK-025 | NLP Training | Chatbot Development | Bob | High | In Progress | 2024-03-10 | 2024-04-15 | 36 | 40 | Due Soon | Training data collection
TSK-026 | Template Engine | Email Marketing | Charlie | Medium | Completed | 2024-01-15 | 2024-02-10 | 26 | 100 | Completed | Drag-drop builder
TSK-027 | Video Encoding | Video Platform | Diana | Critical | In Progress | 2024-03-01 | 2024-04-30 | 60 | 15 | Due Soon | Codec issues
TSK-028 | Smart Contract | Blockchain Integration | Eve | Critical | Not Started | 2024-05-15 | 2024-07-15 | 61 | 0 | Due Soon
TSK-029 | Feed Algorithm | Social Media App | Frank | High | In Progress | 2024-02-15 | 2024-03-30 | 44 | 55 | Due Soon | ML model training
TSK-030 | Tracking Module | Supply Chain Tool | Grace | Medium | In Progress | 2024-03-05 | 2024-04-05 | 31 | 45 | Due Soon | GPS integration
Formulas:
Due Status = IF([Status]="Completed","Completed",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]-TODAY()<=3,"Due Soon","On Track")))

## Team Members
TEAM MEMBERS & RESOURCE ALLOCATION
Member ID | Name | Role | Department | Email | Tasks Assigned | Tasks Completed | Utilization % | Status
MEM-001 | Alice Brown | Senior Developer | Engineering | alice@company.com | 4 | 3 | 80 | Available
MEM-002 | Bob Smith | Full Stack Developer | Engineering | bob@company.com | 3 | 2 | 60 | Available
MEM-003 | Charlie Davis | Backend Developer | Engineering | charlie@company.com | 3 | 2 | 60 | Available
MEM-004 | Diana Lee | Frontend Developer | Engineering | diana@company.com | 3 | 1 | 60 | Available
MEM-005 | Eve Wilson | DevOps Engineer | Engineering | eve@company.com | 3 | 1 | 60 | Available
MEM-006 | Frank Miller | QA Engineer | Engineering | frank@company.com | 2 | 1 | 40 | Available
MEM-007 | Grace Taylor | UI/UX Designer | Design | grace@company.com | 3 | 2 | 60 | Available
MEM-008 | Henry Anderson | UX Researcher | Design | henry@company.com | 2 | 1 | 40 | Available
MEM-009 | Ivan Thomas | Database Admin | Engineering | ivan@company.com | 2 | 0 | 0 | Available
MEM-010 | Julia Martinez | Data Engineer | Engineering | julia@company.com | 2 | 0 | 0 | Available
MEM-011 | Kevin Garcia | Mobile Developer | Engineering | kevin@company.com | 2 | 0 | 0 | Available
MEM-012 | Lisa Robinson | Project Manager | PMO | lisa@company.com | 5 | 2 | 100 | Busy
MEM-013 | Mike Johnson | Senior PM | PMO | mike@company.com | 4 | 1 | 80 | Busy
MEM-014 | Nancy White | Product Owner | Product | nancy@company.com | 3 | 1 | 60 | Available
MEM-015 | Oscar Harris | Business Analyst | Product | oscar@company.com | 2 | 1 | 40 | Available

## Milestones
PROJECT MILESTONES
Milestone ID | Milestone Name | Project | Target Date | Actual Date | Status | Days Variance | Notes
MS-001 | Design Approval | Website Redesign | 2024-01-30 | 2024-01-28 | Completed | -2 | Approved early
MS-002 | Beta Release | Mobile App v2.0 | 2024-04-01 |  | In Progress |  | On schedule
MS-003 | Go Live | Website Redesign | 2024-04-30 |  | Pending
MS-004 | Data Migration Complete | Data Migration | 2024-03-15 |  | Delayed |  | Timeline extended
MS-005 | UAT Sign-off | CRM Integration | 2024-05-15 |  | Pending
MS-006 | Phase 1 Launch | E-commerce Platform | 2024-05-01 |  | Pending
MS-007 | Security Certification | Cloud Migration | 2024-06-30 |  | Pending
MS-008 | Final Delivery | Analytics Dashboard | 2024-03-31 |  | In Progress |  | 90% complete
MS-009 | API v1.0 Release | API Development | 2024-04-15 |  | Pending
MS-010 | Research Report | UX Research | 2024-03-01 |  | In Progress |  | Draft ready
MS-011 | Performance Benchmark | Database Optimization | 2024-04-30 |  | Pending
MS-012 | Pilot Launch | Training Platform | 2024-08-01 |  | Pending
MS-013 | Hardware Integration | Inventory System | 2024-03-30 |  | Delayed |  | Vendor delay
MS-014 | PCI Compliance | Payment Gateway | 2024-03-31 |  | In Progress |  | Audit scheduled
MS-015 | MVP Release | Chatbot Development | 2024-05-30 |  | Pending
MS-016 | Platform Launch | Video Platform | 2024-08-15 |  | Delayed |  | Technical challenges
MS-017 | Mainnet Deployment | Blockchain Integration | 2024-10-01 |  | Pending
MS-018 | Public Beta | Social Media App | 2024-05-15 |  | Pending
MS-019 | Warehouse Pilot | Supply Chain Tool | 2024-05-30 |  | Pending
MS-020 | Regulatory Approval | Compliance System | 2024-04-30 |  | In Progress |  | Documentation ready

## Time Log
TIME TRACKING LOG
Date | Team Member | Project | Task | Hours | Billable | Rate ($/hr) | Amount ($) | Notes
2024-03-01 | Alice Brown | Website Redesign | Checkout Flow | 8 | Yes | 125 | 1000 | Payment integration
2024-03-01 | Bob Smith | Mobile App v2.0 | User Authentication | 7 | Yes | 110 | 770 | OAuth setup
2024-03-01 | Charlie Davis | CRM Integration | Data Sync Module | 8 | Yes | 115 | 920 | API testing
2024-03-01 | Diana Lee | Mobile App v2.0 | UI Components | 6 | Yes | 105 | 630 | Design system
2024-03-02 | Alice Brown | Payment Gateway | Transaction Logging | 7 | Yes | 125 | 875 | Audit trail
2024-03-02 | Eve Wilson | Cloud Migration | Server Setup | 8 | Yes | 130 | 1040 | AWS config
2024-03-02 | Frank Miller | Security Audit | Penetration Testing | 6 | Yes | 100 | 600 | Vulnerability scan
2024-03-03 | Grace Taylor | UX Research | User Interviews | 5 | Yes | 95 | 475 | 5 interviews
2024-03-03 | Henry Anderson | UX Research | Persona Development | 7 | Yes | 90 | 630
2024-03-03 | Ivan Thomas | Database Optimization | Query Analysis | 8 | Yes | 120 | 960 | Slow queries
2024-03-04 | Julia Martinez | Data Migration | Schema Migration | 8 | Yes | 115 | 920 | Data mapping
2024-03-04 | Kevin Garcia | Inventory System | Barcode Scanner | 7 | Yes | 110 | 770 | Hardware testing
2024-03-04 | Lisa Robinson | Website Redesign | Project Management | 4 | Yes | 140 | 560 | Sprint planning
2024-03-04 | Mike Johnson | Mobile App v2.0 | Architecture Review | 3 | Yes | 150 | 450 | Tech lead review
2024-03-05 | Alice Brown | Website Redesign | Checkout Flow | 8 | Yes | 125 | 1000 | Stripe API
2024-03-05 | Bob Smith | Chatbot Development | NLP Training | 7 | Yes | 110 | 770 | Dataset prep
2024-03-05 | Charlie Davis | Analytics Dashboard | Report Generation | 8 | Yes | 115 | 920 | Chart library
2024-03-05 | Diana Lee | Social Media App | Feed Algorithm | 6 | Yes | 105 | 630 | ML model
2024-03-06 | Eve Wilson | Cloud Migration | Network Config | 8 | Yes | 130 | 1040 | VPC setup
2024-03-06 | Frank Miller | CRM Integration | Testing | 7 | Yes | 100 | 700 | QA testing
2024-03-06 | Grace Taylor | Website Redesign | Product Pages | 6 | Yes | 95 | 570 | UI design
2024-03-06 | Henry Anderson | Website Redesign | Usability Testing | 5 | Yes | 90 | 450 | User testing
2024-03-07 | Ivan Thomas | Database Optimization | Index Creation | 8 | Yes | 120 | 960 | Performance
2024-03-07 | Julia Martinez | Data Migration | Data Validation | 7 | Yes | 115 | 805 | Data quality
2024-03-07 | Kevin Garcia | Supply Chain Tool | Tracking Module | 8 | Yes | 110 | 880 | GPS API
|  |  | TOTAL: | 170 |  |  | 19325

## Reports
PROJECT REPORTS & ANALYSIS
PROJECT STATUS SUMMARY
Status | Count | Percentage
In Progress | 19 | 76%
Completed | 3 | 12%
Planning | 3 | 12%
On Hold | 0 | 0%
Cancelled | 0 | 0%
PROJECT HEALTH REPORT
Health Status | Count | Percentage
On Track | 19 | 76%
At Risk | 3 | 12%
Delayed | 3 | 12%
TASK STATUS SUMMARY
Task Status | Count | Percentage
Not Started | 5 | 16.67%
In Progress | 20 | 66.67%
Completed | 5 | 16.67%
On Hold | 0 | 0%
Cancelled | 0 | 0%
RESOURCE UTILIZATION BY DEPARTMENT
Department | Members | Avg Utilization
Engineering | 9 | 40
Design | 2 | 50
PMO | 2 | 90
Product | 2 | 50

## Charts
PROJECT VISUALIZATION

## Instructions
HOW TO USE PROJECT TRACKER PRO
Step 1 | Set Up Your Projects | Go to 'Project List' sheet and enter your project details. Use the dropdown menus for Status and Health fields.
Step 2 | Add Team Members | Navigate to 'Team Members' sheet and add your team. Assign roles and departments using dropdown menus.
Step 3 | Create Tasks | In 'Task Tracker', add all project tasks. Assign to team members, set priorities, and define start/due dates.
Step 4 | Track Time | Use 'Time Log' to record daily hours. Mark billable hours and the system will calculate amounts automatically.
Step 5 | Set Milestones | Add key project milestones in 'Milestones' sheet. Track target vs actual dates and monitor variance.
Step 6 | Monitor Dashboard | Check 'Dashboard' for real-time project status. KPIs update automatically based on your data.
Step 7 | Review Reports | Visit 'Reports' for status summaries and resource utilization analysis.
Step 8 | Customize Settings | Modify dropdown options, add new categories, and adjust the template to fit your workflow.
PRO TIPS:
• Use color-coded status fields to quickly identify project health at a glance
• Set up recurring tasks for ongoing activities to save time
• Review the Dashboard daily to stay on top of project progress
• Use the Time Log to track billable hours for accurate client invoicing
• Monitor resource utilization to prevent team burnout
• Export Charts sheet as images for stakeholder presentations